## Sheet1
Modules | Pages | UI | API | DB | Integration | Testing | Total Progress | Projected Completion Date | Remarks
Donor | Donor Registration | 90 | 90 | 90 | 90 | 20 | 76 | 2025-09-30
| Donor Lists | 90 | 90 | 90 | 90 | 20 | 76 | 2025-09-30
| Donor Details | 90 | 90 | 90 | 90 | 20 | 76 | 2025-09-30
| Donor Edit | 50 | 20 | 80 | 20 | 0 | 34 | 2025-09-30
| Donor Donation History | [6 empty] | 2025-10-07
ß
Admin | Blood Bag Types Entry | [6 empty] | 2025-09-30
Collection | Bag Entry | [6 empty] | 2025-10-07
| Collection List | [6 empty] | 2025-10-07 | DonorID, BagType, Bag Volume, Inward Date
| Segment Blood Grouping | [6 empty] | 2025-10-14
| Blood Processing | [6 empty] | 2025-10-14
| Components Volume | [6 empty] | 2025-10-14
| Validation | [6 empty] | 2025-10-21
| Donation Certificate Generation | [6 empty] | 2025-10-28
Camp | Camp Registraion | [6 empty] | 2025-10-14 | Name, Contact Person, Expected Donors, Total Beds, Date and Time, Start Time End Time, Address,
| Camp Listing | [6 empty] | 2025-10-14
Grouping | Forward Reverse Grouping Entry | 90 | 40 | 20 | 0 | 0 |  | 2025-10-07
| Phenotyping | [6 empty] | 2025-10-14
| Validation | [6 empty] | 2025-10-14
TTI | Hiv, HVsAB HCV | 80 | [5 empty] | 2025-10-07
| VDRL and MP | [6 empty] | 2025-10-14
| Validation | [6 empty] | 2025-10-14
Admin | Dashboard | 30 | [5 empty] | 2025-10-21
| User Registration | [6 empty] | 2025-10-28
| User Roles | [6 empty] | 2025-10-28
| Blood Bank Registration | [6 empty] | 2025-10-21
| Add Inventory | [6 empty] | 2025-10-21
General | Home Page | [6 empty] | 2025-10-21
| Menu | [6 empty] | 2025-09-30
Settings | Blood Pricing | [6 empty] | 2025-10-21
| Donor Report/Cerfificate Settings | [6 empty] | 2025-10-28 | Name, Donation ID, Date of Donation, Dear, Thank you for... With Logo and Signature
| Label Printing | [6 empty] | 2025-10-28 | Single, Multiple (By Range), Multiple (By Date)